## Sheet1
Responsible area
Group | # | Task or function | Legal | Product | Data Ops | Finance | Client Services | Platform | Engineering Teams | Depends On | In Progress
A | 1 | Create a Standard Authentication and Authorization Model | [5 empty] | X |  |  | Yes
A | 2 | Enforce Application Access and Feature Selection (Authorization) | [6 empty] | X | 10
A | 3 | Enforce Content Licensing | [5 empty] | X |  | 10
A | 4 | Enforce Tiers (at runtime) | [5 empty] | X | X | 10
B | 5 | Create Application Catalog |  | X |  |  |  |  | X
B | 6 | Define Feature sets for Applications |  |  |  |  | X |  | X | 5
B | 7 | Create Content Licensing schema |  | X |  |  |  | X |  | 6
B | 8 | Define Tiers (Service Levels) per Application Feature |  |  |  | X |  |  | X | 7
B | 9 | Create the Provisioning Manager tool | [5 empty] | X |  | 5, 6, 7
B | 10 | Provide the master Delivery Catalog for Applications and Content | [5 empty] | X |  | 5, 6, 7
C | 11 | Create the Application Provisioning Contract (for automatic provisioning) | [5 empty] | X
C | 12 | Register Applications, Features and Tiers in the Provisioning Manager | [6 empty] | X | 9
C | 13 | Create Resource Provisioning Routines and register them in the Provisioning Manager | [6 empty] | X | 11
C | 14 | Validate the Bill of Materials before invoking the Resource Provisioning Routines |  |  |  |  | X |  |  | 11, 12, 13
C | 15 | Maintain the Contract and Add/Remove Features | X |  |  |  | X |  |  | 14
D | 16 | Create and maintain the Packaging model |  | X | [5 empty] | 10
D | 17 | Add the Bill of Materials to the Contract in a machine-readable format | X | X | [5 empty] | 10
D | 18 | Translate the Packagintg model to the Delivery Catalog |  | X |  |  | X |  |  | 10
E | 19 | Define Pricing of Application Features and Tiers |  | X |  | X |  |  |  | 10
E | 20 | Create a Billable Activity Contract for Applications | [5 empty] | X
E | 21 | Generate Application Activity Metrics | [6 empty] | X | 20
E | 22 | Aggregate Activity Metrics for Billing |  |  | X |  |  |  |  | 21